## Sheet1
Title | InventoryManagement for a Business
Project statement and outcomes | This project will enable the learner to design an inventory management software for a business. They would be able to create an application from scratch, add products, variants, and optimize it for different scenarios. To implement this project, one must know the basics of database design and full stack application development.
Modules to be implemented |  |  |  | Evaluation template (refer enclosed sample), please share the milestone and module output mapping.
Foundational Module (FM) Allows users to see the hosted website landing page. /home Allows users to register using email and login. Features List: FF1 Implement basic site structure with landing page at /home. Host and redirect to /home. FF3 Implement registration flow and all fail scenarios. FF4 Implement login flow and all fail scenarios. FF5 Upgrade /home while logged in to sign out. FB1 MongoDB desgin and setup database (Users, Roles) FB2 API development for user management (login, registration) FB3 API development for role management | Inventory Module (IM) Allows users to, browse item collection. search/filter/sort item collection. view details of a item. (images, description and reviews) Features List: IF1 Implement item listing page IF2 Implement the search functionality IF3 Integrate filters to search functionality IF4 Integrate sorting to search functionality (no backend needed) IF5 Implement Product details page. IB1 Mongodb design and setup IB2 API Development for Item CRUD IB3 Upgrade for role based CRUD IB4 Implement fine-grained search functionality on items IB5 API Development for image management | Admin Module (AM) Allows onwer role users to manage website. By adding or removing items. By updating the product details and stock. By managing the inventory of stock By generating weekly, monthly reports for inventory movement Features List (role based) AF1 Redirect owner to Admin module on successful login AF2 Implement item management page to view all items. AF3 Implement sorting of items on all criteria AF4 Implement owners UX to create/ update/ delete items will all details and images and availability count. AF5 Implement weekly, monthly reports for inventory movement | Features List (role based) AB1 Implement create on item AB2 Implement update on item. AB3 Implement delete and soft delete on item. AB4 Implement report generation | Milestone1 - Version0 When - at the end of 2nd week Input criteria - Approved 2nd week deliverables Exit criteria - Approved First demo of Server User puts URL in browser Able to register Able to login - Tagging code in version control | Milestone2 - Version1 When - at the end of 4th week Input criteria - Approved 4th week deliverables Exit criteria - Approved second demo of Server All previous demo features Able to browse through items Able to sign out - Tagging code in version control | Milestone3 - Version2 When - at the end of 6th week Input criteria - Approved 6th week deliverables Exit criteria - Approved third demo of Server All previous demo features Admins able to manage items All users able to search and filter and sort items All users able to reach /admin through login - Tagging code in version control | Milestone4 - VersionFinal When - at the end of 8th week Input criteria - Approved 8th week deliverables Exit criteria - Approved Final demo of Server All previous demo features Able to generate all reports Admins able to manage item image All users able to access all features - Tagging code in version control
Week-wise module implementation and high-level requirements with output screenshots
Week1 All: - Understanding project architecture - Competency gap analysis - Competency plan and actions - Understanding sequence - Group assignments - Making env ready with tools FM - Designing URL endpoints - Test strategy - Wireframing Tasks module IM+AM - Designing Public API - Test strategy Deliverables - Approved API - Approved Test strategy | Week2 FM: - Creation of project structure in version control system - Implementation of stub for IM and AM based on API - Implementation of FF1, FF3, FF4 - Implementation of FB1, FB2 - Implementing automated test IM + AM: - Creation of project structure in version control system - Implementing stubs for all features Deliverables: - github code - peer and external reviewed - Module test coverage and report | Week3 FM: - Implementation of FF5 - Implementation of FB3 - Implementing automated test IM+AM: - Design UX for IF1 through IF5 - Implementing automated test Deliverables: - github code - external reviewed - Module test coverage and report | Week4 IM: - Implementation of IB1 - Implementation of IB2 and IF1 - Implementation of IB3 - Implementation of IB4 - Implementing automated test FM + AM - Implementation of AF1 - Regression testing Deliverables: - github code - external reviewed - Module test coverage and report | Week5 SM: - Implementation of IF2, IF3 and IF4 - Implementation of IF5 and IB5 - Implementing automated test AM: - Implementing AB1, AB2 - Implementing AF2, AF3 - Implementing automated test FM: - Regression testing Deliverables: - github code - external reviewed - Module test coverage and report | Week6 FM: - Regression testing SM: - Regression testing - Implementing automated test AM: - Implementing AF4 and AB3 - Implementing AF5 and AB4 - Implementing automated test Deliverables: - github code - external reviewed - Module test coverage and report | Week7 FM: - Integration - Executing smoke test (main use cases) - Executing System test - Defect fixing IM+AM: - Updating system test cases - Defect fixing Deliverables: - github code - external reviewed - ST test cases and report(excel) - Defect report(excel) | Week8 SM: - Executing System test - Defect fixing - Packaging and Deployment FM+AM: - Creating Acceptance test cases - Defect fixing - Testing AT Deliverables: - approved Final code in github - AT report
Design diagrams (class diagrams/flow charts/DB design etc)